## Sprint Backlog sprint 3
12 | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
GOAL: "An awesome Trux application" Started: 23-03-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 0 | 0 | 0
Check Statistics | 350 | 360 | 0 | Design Simple UI's | 20 | Dennis, Niklas, Aman | Done | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6
|  |  |  | Design Rich UI's | 40 | Dennis, Niklas, Aman | Done | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6
|  |  |  | Design Database | 85 | Ivo, Jerker, Jonas | Done | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6
|  |  |  | Design Server | 85 | Ivo, Jerker, Jonas | Done | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6
|  |  |  | Receive data | 60 | Dennis, Niklas, Aman | Done | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6
|  |  |  | Exchange data with server | 60 | Ivo, Jerker, Jonas | Done | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6
| 0 | 0 | 0 |  |  |  | TODO
TODO
TODO
| 0 | 0 | 0 |  |  |  | TODO
TODO
TODO
TODO
TOTAL | 350 | 360 | 0 |  |  |  |  | 36 | 36 | 36 | 36 | 36 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 0 | 0
Daily burnout | -10 | [6 empty] | 36 | 36 | 36 | 36 | 36 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 350 | 314 | 278 | 242 | 206 | 170 | 170 | 170 | 134 | 98 | 62 | 26 | 0 | 0 | 0
Total time left (from spent) | [5 empty] | Burnout | 360 | 324 | 288 | 252 | 216 | 180 | 180 | 180 | 144 | 108 | 72 | 36 | 0 | 0 | 0
Complexity (story points) | 31

## Sprint Backlog sprint 4
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
GOAL: "An awesome Trux application" Started: 20-01-2014 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 0 | 0 | 0
Supervisor see performance & compare statistics | 260 | 213 | 47 | User login features | 140 | Ivo, Jerker, Jonas | Done | 16 | 16 | 16 | 16 | 16 |  |  | 16 | 16 | 16 | 16 | 10
|  |  |  | Group/Company features | 20 | Jonas, Jerker | Done | 0 | 1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | Compare driver/group | 40 |  | TODO | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | Register features | 60 | Ivo, Jonas, Dennis | Done | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 4
Drivers see performance & compare statistics | 20 | 20 | 19 | Compare friend/group | 20 | Niklas, Aman | Done | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Check Statistics | 80 | 136 | 0 | Charts and averages | 80 | Niklas, Aman, Jerker, Dennis, Jonas | Done | 14 | 14 | 14 | 14 | 14 |  |  | 14 | 14 | 14 | 14 | 10
TOTAL | 360 | 369 | 66 |  |  |  |  | 37 | 37 | 36 | 36 | 36 | 0 | 0 | 36 | 36 | 36 | 36 | 24 | 0 | 0
Daily burnout | 0 | [6 empty] | 36 | 36 | 36 | 36 | 36 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 360 | 324 | 288 | 252 | 216 | 180 | 180 | 180 | 144 | 108 | 72 | 36 | 0 | 0 | 0
Total time left (from spent) | [5 empty] | Burnout | 369 | 332 | 295 | 259 | 223 | 187 | 187 | 187 | 151 | 115 | 79 | 43 | 19 | 19 | 19
Complexity (story points) | 31

## Sprint Backlog sprint 5
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
GOAL: "An awesome Trux application" Started: 04-05-2015 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 0 | 0 | 0
Supervisor see performance & compare statistics | 150 | 60 | 90 | Group/Company features | 100 | Aman, Dennis, Ivo, Jerker, Jonas, Niklas | TODO
|  |  |  | See driver statistics | 50 | Aman, Dennis, Niklas | Working | Work Done per day per task [Hours] 1: 12; Work Done per day per task [Hours] 2: 12; Work Done per day per task [Hours] 3: 12; Work Done per day per task [Hours] 4: 12; Work Done per day per task [Hours] 5: 12
Driver/Supervisor: I want to communicate with my friends/drivers. | 60 | 126 | 0 | Friends (requests etc) | 30 | Aman, Dennis, Ivo, Jerker, Jonas, Niklas | Done | Work Done per day per task [Hours] 1: 12; Work Done per day per task [Hours] 2: 12; Work Done per day per task [Hours] 3: 12; Work Done per day per task [Hours] 4: 12; Work Done per day per task [Hours] 5: 12; Work Done per day per task [Hours] 8: 6; Work Done per day per task [Hours] 9: 12; Work Done per day per task [Hours] 12: 6
|  |  |  | Messages | 30 | Aman, Dennis, Ivo, Jerker, Jonas, Niklas | Working | Work Done per day per task [Hours] 8: 6; Work Done per day per task [Hours] 9: 6; Work Done per day per task [Hours] 10: 6; Work Done per day per task [Hours] 11: 12; Work Done per day per task [Hours] 12: 12
Check statistics | 10 | 0 | 0 | Start and end of driving sessions | 10 | Jonas, Jerker, Ivo | TODO
- | 20 | 20 | 0 | Contact window | 20 | Aman | Working | Work Done per day per task [Hours] 5: 2; Work Done per day per task [Hours] 10: 6; Work Done per day per task [Hours] 11: 6; Work Done per day per task [Hours] 12: 6
Driver: I want to see where my friends are AND Supervisor: I want to see where my drivers are | 175 | 126 | 49 | Integrate map and GPS | 70 | Niklas, Dennis, Aman | Working | Work Done per day per task [Hours] 1: 6; Work Done per day per task [Hours] 2: 6; Work Done per day per task [Hours] 3: 6; Work Done per day per task [Hours] 4: 6; Work Done per day per task [Hours] 5: 6; Work Done per day per task [Hours] 8: 12
|  |  |  | Show friends / drivers on map | 90 | Niklas, Dennis, Aman | Working | Work Done per day per task [Hours] 9: 12; Work Done per day per task [Hours] 10: 12; Work Done per day per task [Hours] 11: 12; Work Done per day per task [Hours] 12: 6
|  |  |  | Store location data | 15 | Ivo, Jerker, Jonas | Working | Work Done per day per task [Hours] 8: 12; Work Done per day per task [Hours] 9: 6; Work Done per day per task [Hours] 10: 12; Work Done per day per task [Hours] 11: 6; Work Done per day per task [Hours] 12: 6
TOTAL | 415 | 332 | 139 |  |  |  |  | 30 | 30 | 30 | 30 | 32 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 0 | 0
Daily burnout | 55 | [6 empty] | 36 | 36 | 36 | 36 | 36 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 415 | 379 | 343 | 307 | 271 | 235 | 235 | 235 | 199 | 163 | 127 | 91 | 55 | 55 | 55
Total time left (from spent) | [5 empty] | Burnout | 332 | 302 | 272 | 242 | 212 | 180 | 180 | 180 | 144 | 108 | 72 | 36 | 0 | 0 | 0
Complexity (story points) | 31

## Sprint Backlog sprint 6
| Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | Work Done per day per task [Hours]
GOAL: "Recommendation Engine prototype and Simple Authentication" Started: 20-01-2014 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 0 | 0 | 0
Driver/Supervisor: I want to communicate with my friends/drivers. | 36 | 48 | 0 | Messages | 18 | Ivo, Jonas, Dennis | Working | Work Done per day per task [Hours] 1: 8; Work Done per day per task [Hours] 2: 8; Work Done per day per task [Hours] 3: 8
|  |  |  | Friends (requests etc) | 18 | Jerker, Jonas | Working | Work Done per day per task [Hours] 1: 8; Work Done per day per task [Hours] 2: 8; Work Done per day per task [Hours] 3: 8
Driver: I want to see where my friends are AND Supervisor: I want to see where my drivers are | 0 | 0 | 0 | Show friends on map
Store locations
| 10 | 6 | 0 | Stable minimize/resume | 10 |  |  | Work Done per day per task [Hours] 4: 6
Promote driver safety | 30 | 24 | 0 | Adaptable user interface | 30 |  |  | Work Done per day per task [Hours] 1: 6; Work Done per day per task [Hours] 2: 6; Work Done per day per task [Hours] 3: 6; Work Done per day per task [Hours] 4: 6
| 0 | 0 | 0
TOTAL | 76 | 78 | 0 |  |  |  |  | 22 | 22 | 22 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily burnout | -284 | [6 empty] | 36 | 36 | 36 | 36 | 36 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 76 | 40 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from spent) | [5 empty] | Burnout | 78 | 56 | 34 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complexity (story points) | 31

## Product Backlog
Priority | Story Points | Sprint | ID | User Type | Wants to... | So that... | So that...
1 | 8 | 1 | D4 | Truck driver | Have a simple and intuative GUI... |  | It doesn't distract me while I'm driving.
2 | 8 | 2 | D1 | Truck driver | Be able to see statistics of how I'm performing... |  | I can improve.
3 | 8 | 2 | S1 | Supervisor | Be able to see statistics of how my drivers are performing... |  | I can help them improve.
4 |  |  | D2 | Truck driver
5 |  |  | D6 | Truck driver
6 |  |  | S2 | Supervisor
7 |  |  | S5 | Supervisor
8 |  |  | S6 | Supervisor
9 |  |  | C1 | Company
10 |  |  | C2 | Company
11 |  |  | S4 | Supervisor
12 |  |  | D3 | Truck driver
13 |  |  | D7 | Truck driver
14 |  |  | D8 | Truck driver
15 |  |  | D5 | Truck driver
16 |  |  | S3 | Supervisor
Past stories
| 5 | 1 |  | Developer | Get all tools working on local machine
| 5 | 1 |  | Configuration Manager | List infrastructure to deploy the application | the code can run

## User types
Truck driver
User
Supervisor
Company
System administrator

## Team members
| Working hours per day | Note: originally here was a list of all team members, which you could assign to task. It's better to freely write who is assigned to tasks because we may assign more than one person. The number here is still used to estimate how much should be accomplished per day.
Whole team | 36

## Task statuses
TODO
Working
Done
Blocked
Verify